## Sheet1
Sprint | Week | Focus | Tasks
Sprint 1 | Week 1 | Setup & Initial Tasks | - Define project title: "Dynamic Price Prediction in E-Commerce Application".
- Set up Git repository and configure JIRA login.
- Create initial epic for Dynamic Price Prediction.
- Draft user stories for real-time price updates, competitor monitoring, and admin notifications.
- Estimate story points for each user story.
- Plan major milestones and deliverables for Sprint 1.
- Create basic project timeline for all 3 sprints.
- Assign roles and define communication plan.
| Week 2 | Design & Development | - Detail scope for price updates, notifications, and competitor monitoring.
- Elaborate on use cases for features (e.g., monitoring competitor prices).
- Refine user stories and ensure adherence to INVEST criteria.
- Review and adjust story points.
- Develop Class and Sequence diagrams for price synchronization and competitor monitoring.
- Set up Sprint Burndown and Velocity charts.
- Begin task tracking and maintain Sprint board in JIRA.
| Week 3 | Testing & Review | - Test price synchronization and competitor monitoring features.
- Conduct code reviews to ensure quality.
- Create Level 0, Level 1, and Level 2 DFDs for features.
- Create test cases and begin executing tests.
- Prepare for Review 1 by refining user stories and completing UML diagrams.
Sprint 2 | Week 4 | Feature Implementation | - Detail scope for demand forecasting and inventory-based pricing adjustments.
- Define use cases and refine user stories.
- Implement demand forecasting algorithms.
- Align story point estimations with real-world tasks.
- Refine Class diagrams to include forecasting and pricing adjustments.
- Update Sequence diagrams.
- Update Sprint Burndown and Velocity charts.
- Track progress in JIRA.
| Week 5 | Testing & Integration | - Test demand forecasting and inventory-based pricing adjustments.
- Review and ensure code quality.
- Update Class diagrams and create Component diagrams for pricing adjustments.
- Assess Sprint velocity and adjust tasks accordingly.
- Create and execute test cases.
- Prepare for Review 2 by completing DFD documentation.
| Week 6 | Finalization & Review | - Finalize feature development and refine code quality.
- Complete Level 0, Level 1, and Level 2 DFDs.
- Ensure all user stories are completed and tests executed for Review 2.
Sprint 3 | Week 7 | Feature Development | - Detail scope for geo-targeted and personalized pricing, along with flexible payments.
- Develop user stories and ensure adherence to INVEST criteria.
- Update Class diagrams for geo-targeted and personalized pricing.
- Develop new Sequence diagrams for customer interactions.
- Continue updating Burndown and Velocity charts.
- Maintain Sprint board in JIRA.
| Week 8 | Testing & Integration | - Test geo-targeted pricing, personalized pricing, and flexible payment features.
- Ensure code quality for final integrations.
- Review Burndown chart and velocity for progress.
- Execute tests for geo-targeted pricing, personalized pricing, and flexible payments.
- Refine user stories and UML diagrams.
| Week 9 | Final Testing & Review | - Conduct final testing for all features and ensure everything is code complete.
- Test the entire system for functionality and performance.
- Prepare for Review 2 with completed features, DFDs, and tests.
- Review and adjust the project as needed.
Final Week (End of Sprint 3) | - | Performance Testing, JIRA Closure, Documentation | - Automate test suite for regression testing.
- Measure performance metrics for system stability.
- Ensure all features are completed with high-quality code metrics.
- Close all stories in JIRA and ensure sprint completion.
- Complete documentation and prepare a retrospective analysis.
- Ensure all tasks are closed in JIRA.